## Instructions
7.3 Corrective Action Registry Template
INTRODUCTION
Corrective actions need to be tracked and logged in order for you to build towards your improvement planning for each. Having a consolidated document with all of your corrective actions (Tool 7.2) can help you manage all violations, notice patterns in where your company is falling short of social compliance standards, and track progress. This Corrective Action Registry Matrix is designed to help your company’s day-to-day management of violations, while the Improvement Plan – included later in this chapter – is designed for longer-term progress tracking and planning. Use this template as a cover sheet to compile the individual Correction Action Plan forms at your company. This is a handy reference to give you a quick overview of outstanding issues, progress being made and where to focus your attention. During internal audits (Tool 6.1) and management reviews (Tool 1.2), you should review this document so you are aware of outstanding issues.
INSTRUCTIONS
Use the matrix on the "Template" tab to log all of your corrective actions logged using the Corrective Action Template (tool 7.2). You can adapt it to fit your company’s needs. We have provided a sample corrective action table in the "Sample" tab.

## Template
Corrective Action Registry Matrix
Corrective Action # | Planned Start Date | Social Compliance System Element | Problem Summary | Corrective Action Summary | Manager Responsible | Due Date | Progress Update | Status | Date Closed

## Sample
Corrective Action Registry Sample
Corrective Action # | Planned Start Date | Social Compliance System Element | Problem Summary | Corrective Action Summary | Manager Responsible | Due Date | Progress Update | Status | Date Closed
352 | 2022-01-02 | OHS | Risk of injury from drills and saws | 1. Purchase protective gloves 2. Train Workers 3. Install machine guards 4. Update procedures | John Doe | 2022-01-31 | 10 Jan – gloves purchased, training scheduled 31 Jan - training delivered, guards installed | Closed | 2022-02-15